## Instructions
Column | Instructions For Completing This Document
Complete the Project Name, NC, Project Manager Name, and Project Description fields
For each issue identified, complete the following:
A | ID: A unique ID number used to identify the issue in the issue tracking log.
B | Current Status: This column should be populated with the issue's current status. o Open: The issue is currently open but has not yet been addressed. o Work In Progress: The issue is being actively worked to develop a resolution. o Closed: The issue is no longer considered an active project threat and can be closed with or without resolution. Some other potential options include: o Late: The issue resolution is not yet resolved and it is past the expected resolution date. o On Hold: The issue has been put on hold. o Combined: Two issues found to be similar have been combined.
C | Priority: This column should be populated with the priority of the issue. Valid options include the following: High, Medium, Low. These are defined as follows: o Critical: Issue will stop project progress if not resolved. o High: Issue will likely move the project back in terms of budget or timeline, or will materially affect quality or scope. o Medium: Issue will have material effect on project, has potential to be moved to high category and/or requires significant resources to manage. o Low: Issue is expected to have a moderate effect on the project, but will require resources to address.
D | Issue Description: This column should be populated with a description of the issue.
E | Assigned to Owner: This column should be populated by the name of the issues owner. The individual most responsible for working towards resolving the issue.
F | Expected Resolution Date: This column should be populated with the date that the issue is expected to be resolved.
G | Escalation Required (Y/N): This column should be populated with “Yes” if the program/project manager feels an issue needs to be escalated and “No” if escalation is not needed to resolve the issue.
H | Impact Summary: This column should be populated with a description of the impact of the issue. The impact may be expressed in terms of one or more of the following: schedule, scope, resources, and space. The impact description should also include a reference to any milestones impacted.
I | Action Steps: This column should be populated with the proposed steps to address the issue. Examples include, but are not limited to, developing alternatives analysis or submitting a change request.
J | Issue Type: This column should be populated with the issue type. Valid options include the following: FRI, Procedural, System, Other. These are defined as follows: o Informational: The issue was generated and logged in response to a request for information external to the immediate project/project team. o Procedural: The issue impacts process or procedure. o System: The issue impacts systems (hardware or software). o Other: The issue impacts other areas.
K | Date Identified: This column should be populated with the date that the issue was identified.
L | Associated ID(s): This column should contain the project ID of any associated milestones that may be impacted by an issue or that the issue is dependant upon for resolution. Please note, this value may require coordination with other program/project managers or the PMA.
M | Entered By: This column should be populated by the name of the individual who first identified the issue.
N | Actual Resolution Date: This column should be populated with the date that the issue was actually resolved.
O | Final Resolution & Rationale: This column should be populated with a description of the final resolution & rationale of the issue. The resolution may be expressed in terms of one or more of the following: schedule, scope, resources, and space. The resolution description should also include a reference to the milestones impacted.
Column | Instructions For Changing the Contents of Drop-Down Menus
B, C G, J | Highlight the cell of which you wish to change the content of the drop down menu. From the file menu click "Data" -> "Validation" and change the content of the source field
Column | Instructions For Filtering Data
Any | Highlight the header of the cell you wish to filter data on From the file menu click "Date" -> "Filter" ->"Auto Filter" Then select your filter criteria from the drop down menu that appears on your header cell

## Template
ISSUE MANAGEMENT LOG | [8 empty] | ISSUE MANAGEMENT LOG
Project Name: |  |  |  | Trans Asia Accpac/VMS/Esourcing Development |  |  |  |  | Project Name: | Trans Asia Accpac/VMS/Esourcing Development
Project Manager Name: |  |  |  | Derrick Lo |  |  |  |  | Project Manager Name: | Derrick Lo
Project Description: |  |  |  | Customiation / Integration of Trans Asia's Procurement System |  |  |  |  | Project Description: | Customiation / Integration of Trans Asia's Procurement System
ID | Current Status | Priority | Module | Issue Description | Assigned To Owner | Expected Resolution Date | Escalation Required (Y/N)? | Impact Summary | Action Steps | Issue Type | Date Identified | Assoc ID | Entered By | Actual Resolution Date | Final Resolution & Rationale
1 | Open |  | VMS | Only the Core Business related to the commodity classification will be available in the "Core Business" drop down. | Ricky |  | N | For estimation of efforts | Add maintenance for commodity filtering | Informational | 2013-07-04 |  | Derrick
2 | closed |  | VMS | Change "Date Started" to "Date Established" | Ricky |  | N |  |  | System | 2013-07-04 |  | Derrick
3 | closed |  | VMS | Change the "Endorsed by" to "Endorsed to" (Endorse to buyer) | Ricky |  | N |  |  | System | 2013-07-04 |  | Derrick
4 | Open |  | VMS | Page 1: Add Vicinity Map near Vendor Address | Ricky |  | N | Low - Recommend Phase 2 |  | System | 41459 |  | Derrick
5 | Open |  | VMS | Q: Maintain Address? ZIP? (City, Brgy) | Ricky |  | Y | Low - Recommend Phase 2 |  | Informational | 41459 |  | Derrick
6 | closed |  | VMS | Contacts – Change label to: CEO/President/GM, Sales/Marketing, Technical/Engineering, Services, Accounting, Credit and Collection | Ricky |  | N |  |  | System | 2013-07-04 |  | Derrick
7 | Open |  | VMS | Page 2 - 2: List for the maintenance of Vendor Category/Sub Category still not final (c/o Marife) | Marife |  | N |  |  | System | 2013-07-04 |  | Derrick
8 | closed |  | VMS | Manpower Resources: Change label "In Sales" to "In Sales and Marketing" | Ricky |  | N |  |  | System | 2013-07-04 |  | Derrick
9 | closed |  | VMS | Remove "Facilities" portion and add another line in No. “3. Assets and Investments". "Add button" | Ricky |  | N |  |  | System | 2013-07-04 |  | Derrick
10 | closed |  | VMS | BIR Registration: TIN -- Add Vat Type "Zero Rated" | Ricky |  | N |  |  | System | 2013-07-04 |  | Derrick
11 | Open |  | VMS | Page4 no.3: change label to "BIR Registration, Sample Invoice and Official Receipt | Ricky |  | N |  |  | System | 2013-07-04 |  | Derrick
12 | Open |  | VMS | Other Permit Attachments – Enable multiple uploads. | Ricky |  | N |  |  | System | 2013-07-04 |  | Derrick
13 | closed |  | VMS | Hide No. 4. For Corporation and partnership and No. 5. Proprietor/Partners/Incorporators | Ricky |  | N |  |  | System | 2013-07-04 |  | Derrick
14 | closed |  | VMS | Legal Structure & Financial information: Increase allowable upload file to 10MB | Ricky |  | N |  |  | System | 2013-07-04 |  | Derrick
15 | closed |  | VMS | Page 5: Change "Attach Financial Statement" to "Attach Latest Audited Financial Statement" | Ricky |  | N |  |  | System | 2013-07-04 |  | Derrick
16 | closed |  | VMS | Main Page: Change Address to "Level 11 Phinma Plaza..." | Ricky |  | N |  |  | System | 2013-07-04 |  | Derrick
17 | closed |  | VMS | Page 2 - 2: Change uploading to multiple files and Change the statement "Please furnish us....If possible, provide, brochures/catalogues/certificate of distributorship" | Ricky |  | N |  |  | System | 2013-07-04 |  | Derrick
18 | Open |  | VMS | page2.2 "select brand" drop down to txtbox. Change major clients to "exclusive distributorship?: dropdown "yes/no" | Ricky |  | N | Low - Recommend Phase 2 |  | System | 2013-07-04 |  | Derrick
19 | closed |  | VMS | Page 1: Remove "Sheet" from "Vendor Information Sheet" | Ricky |  | N |  |  | System | 2013-07-04 |  | Derrick
20 | closed |  | VMS | Page 1: Hide No. "3. Certification & Warranty" | Ricky |  | N |  |  | System | 2013-07-04 |  | Derrick
21 | closed |  | VMS | Page 1: Should have an auto numbered "Authentication No." | Ricky |  | N |  |  | System | 2013-07-04 |  | Derrick
22 | closed |  | VMS | Hide Financial Report and Legal Report under "Commodity Buyer's Evaluation view" | Ricky |  | N |  |  | System | 2013-07-04 |  | Derrick
23 | Open |  | VMS | Change the Hidden Financial Report and Legal Report to: drop down box for the Vendor Group Code which will come from Accpac. | Ricky |  | N | For estimation of efforts |  | System | 2013-07-04 |  | Derrick
24 | Open |  | VMS | Maintain new vendor coding. Identification of Trade and Non-Trade accounts will be the Vendor Group Code. | Vince |  | N |  |  | Procedural | 2013-07-04 |  | Derrick
25 | closed |  | VMS | Hide Financial Report and Legal Report under "Commodity Buyer's Evaluation view" | Ricky |  | N |  |  | System | 2013-07-04 |  | Derrick
26 | Closed |  | VMS | Get Email content and format to be sent to Vendors | Marife |  | N |  |  | System | 2013-07-04 |  | Derrick |  | Already submitted to Ricky. For implementation to System
27 | Open |  | VMS | Ricky to call Gilbert if we can add Authentication system in logging in to Esourcing | Ricky |  | Y | For estimation of efforts |  | Informational | 2013-07-04 |  | Derrick
28 | Open |  | VMS | Sending of notification/authentication of chosen vendor is not yet implemented. System should add activation process the same as social media/email application | Ricky |  | Y | For estimation of efforts |  | System | 2013-07-04 |  | Derrick
29 | Open |  | VMS | Generation of Vendor Import file to Accpac still under development c/o Ricky | Ricky |  | Y |  |  | System | 2013-07-04 |  | Derrick
30 | Open |  | VMS | Checking of Accpac Vendor Import Tool. The tool should not check if the row is blank. | Derrick |  | Y |  |  | System | 2013-07-04 |  | Derrick
31 | Closed |  | VMS | Vendor Code Creation based on the Prefix ""H-"" + First Letter of Vendor + Next Number for Series | Vince |  | Y |  |  | Informational | 2013-07-04 |  | Derrick |  | TAO Will maintain new Vendor Codes. Trade and Non-Trade vendors will be identified by Group Code
32 | closed |  | VMS | Vendor Maintenance Screen: Change "VM Assessment" to "Commodity Buyer" | Ricky |  | N |  |  | System | 2013-07-04 |  | Derrick
33 | closed |  | VMS | Vendor Maintenance Screen: Change "VM Officer" to "Vendor Admin" | Ricky |  | N |  |  | System | 2013-07-04 |  | Derrick
34 | Open |  | Accpac | Lead time should only count working days excluding holidays upon posting. | Derrick |  | Y |  |  | System | 2013-07-04 |  | Derrick
35 | Open |  | Accpac | Expected Arrival date should be the latest date from the line items | Derrick |  | Y |  |  | System | 2013-07-04 |  | Derrick
36 | Open |  | eSourcing | Under Bid Items --PR Details: Expected Arrival Date not updating, Item Code, Not Updating | Ricky |  | N |  |  | System | 2013-07-04 |  | Derrick
37 | Open |  | eSourcing | Budget should be extracted from Accpac | Ricky |  | Y |  | Derrick to give ricky database field | System | 2013-07-04 |  | Derrick
38 | Open |  | eSourcing | Prices Currency should be synched to Accpac | Ricky |  | Y |  | Derrick to give ricky database field | System | 2013-07-04 |  | Derrick
39 | Open |  | eSourcing | Show Incoterms - below item bid price -- Code only; additional tooltip | Ricky |  | N |  |  | System | 2013-07-04 |  | Derrick
40 | Open |  | eSourcing | Show Payment Type, Lead time. In the bid tendered item. Additional tooltip | Ricky |  | N |  |  | System | 2013-07-04 |  | Derrick
41 | Open |  | eSourcing | Change Freight to Deliver Cost to site | Ricky |  | N |  |  | System | 2013-07-04 |  | Derrick
42 | Open |  | eSourcing | Additional: In land Freight and Sea/Air Freight | Ricky |  | N |  |  | System | 2013-07-04 |  | Derrick
43 | Open |  | eSourcing | Currency to be exported from e-soucing to Accpac should be the original tendered currrency | Ricky |  | Y |  | Ricky and Derrick to study linking of Accpac currency | System | 2013-07-04 |  | Derrick
44 | Open |  | Accpac | PO budget checking. PO will be imported to Accpac. Accpac will check per line item if item for PO has budget. | Derrick |  | Y |  | Get efforts from developer: Change the timing of the checking of Budget. Checking of Budget will still be on a per line basis, but this time, checking of budget will be upon posting of the transaction. | System | 2013-07-04 |  | Derrick
45 | Open |  | Accpac | If Line item is within budget, then proceed, If not within budget, then do not add line item. | Derrick |  | Y |  | Get efforts from developer: Change the timing of the checking of Budget. Checking of Budget will still be on a per line basis, but this time, checking of budget will be upon posting of the transaction. | System | 2013-07-04 |  | Derrick
46 | Open |  | Accpac | Should be able to identify who will process the PO. (Base it on the buyer tagged) | Derrick |  | Y
47 | Open |  | Accpac | Workflow to be finalized by Trans Asia Oil c/o Mher | Mher |  | Y
48 | Open |  | eSourcing | Approved PO will reflect in e-sourcing under "awarded bid tenders" | Ricky |  | Y | For estimation of efforts
49 | Open |  | eSourcing | Under awarded Bid Tenders, upon clicking the po Number, a web format of the PO will be displayed with free text [Status/Remarks <- column header] for supplier to update. | Ricky |  | Y | For estimation of efforts
50 | Open |  | Accpac | Request for payment: Did not change description when code is changed. | Derrick |  | Y
51 | closed |  | Accpac | TAO to get back to ssi if will stick to one default GL Account | Derrick |  | Y
52 | closed |  | Accpac | SSI to check with programmer - efforts on making the GL account default | Derrick |  | Y
53 | Open |  | Accpac | PO Invoice Screen - Should Be able to see payments/cms related to a PO. (Kailangan lang malaman kung ilan pa ang balanse.) | Derrick |  | Y
54 | Open |  | Accpac | Set ruling wherein if PO is <> certain amount, system will auto create CM to the bank to issue payment. | Derrick
55 | closed |  | Accpac | Prompt in Request for payment, asking if you want to print PR.